## FINAL LIST TO UPLOAD IN ERP
Party Name | Order No | Date | Descripion | QTY | Qty Billied | Balance Qty | PDC | Unit | REMARKS
LRSAM | DRDL/PGLRSAM/1701/31P/23/210/0230 | 2024-06-20 | Lining of M2B Motor | 4 | 0 | 4 | 2027-12-27 | Adibatla
LRSAM | DRDL/PGLRSAM/1701/31P/23/210/0230 | 2024-06-20 | Lining of M3B Motor | 4 | 1 | 3 | 2027-12-27 | Adibatla
LRSAM | DRDL/PGLRSAM/1701/31P/23/210/0230 | 2024-06-20 | Liner Removal and Relining of Kill Vehicle and and fabrication of Assocated Hardware | 4 | 0 | 4 | 2027-12-27 | Adibatla
LRSAM | DRDL/PGLRSAM/1701/31P/23/210/0230 | 2024-06-20 | Liner removal and Reling of M1B Motor | 4 | 0 | 4 | 2027-12-27 | Adibatla
LRSAM | DRDL/PGLRSAM/1701/31P/23/210/0230 | 2024-06-20 | Liner removal and Reling of M2B Motor | 4 | 0 | 4 | 2027-12-27 | Adibatla
LRSAM | DRDL/PGLRSAM/1701/31P/23/210/0230 | 2024-06-20 | Liner removal and Reling of M3B Motor | 4 | 0 | 4 | 2027-12-27 | Adibatla
RCI | RCI/26SO0081/RM2/RUDRAM-2/CMS-III | 2025-07-07 | Stage Processing Bonding and Machining of Nozzle Liners & Assy. | 3 | 2 | 1 | 2026-07-12 | Adibatla
AADYAH | 2025260100 | 2025-12-08 | Flex Seal Transfer Moulding Tool | 1 | 0 | 1 | 2026-06-06 | Adibatla
AADYAH | 2025260100 | 2025-12-08 | Thermal Boot Transfer Moulding Tool | 1 | 0 | 1 | 2026-06-06 | Adibatla
AADYAH | 2025260100 | 2025-12-08 | Flex Seal Pull test Fixture | 1 | 0 | 1 | 2026-06-06 | Adibatla
ANSP | DRDL/9369/21/15K/2023/2062/2070P | 2023-08-28 | Processing of B2 CRMC | 10 | 5 | 5 | 2026-12-27 | ANSP
ANSP | DRDL/9369/21/15K/2023/2061/2071P | 2023-08-28 | Processing of B1 CRMC | 10 | 7 | 3 | 2028-08-27 | ANSP
ANSP | DRDL/9380/21/15K/2023/2065/2102P | 2023-12-05 | Processing of B3L CRMC | 12 | 9 | 3 | 2026-12-31 | ANSP
ANSP | DRDL/9484/21/15K/2023/2101/2134P | 2024-06-11 | Composite Sleeves of CGG | 20 | 13 | 7 | 2026-06-30 | ANSP
ANSP | DRDL/9485/21/15K/2023/2102/2135P | 2024-06-11 | Casing with liner (CGG) (MK-II) | 10 | 5 | 5 | 2026-06-30 | ANSP
ANSP | DRDL/9485/21/15K/2023/2102/2135P | 2024-06-11 | NE Dome with liner (CGG) (MK-II) | 10 | 5 | 5 | 2026-06-30 | ANSP
ASL | ASL/31/20/4061/17/0100/0226 | 2021-03-09 | Processing of V1C Nozzle Liners Including Machinging | 8 | 4.4 | 3.6 | 2027-03-31 | CPDC
ASL | ASL/31/20/4061/17/0183/0091 | 2021-08-04 | Insulation Rubber Lining for V1C Intermediate Dome & M/c | 8 | 2 | 6 | Send Letter 31-03-2026 | CPDC
ASL | ASL/DD2/R/DD23/0147/20/2579/2539 | 2021-09-20 | Processing ,Machining & Realization of HPS2C Divergent Sub Assembly Nozzle Liners including coomposite profile Machining | 10 | 8.25 | 1.75 | 2026-11-30 | CPDC
ASL | ASL/DD2/R/DD23/0147/20/2579/2539 | 2021-09-20 | Processing ,Machining & Realization of HPS2C Convergent Sub Assembly Nozzle Liners including coomposite profile Machining | 10 | 7.55 | 2.45 | 2026-11-30 | CPDC
ASL | ASL/DD2/R/DD23/0147/20/2579/2539 | 2021-09-20 | Processing ,Machining & Realization of HPS3C Divergent Sub Assembly Nozzle Liners including coomposite profile Machining | 10 | 8.6 | 1.4 | 2026-11-30 | CPDC
ASL | ASL/DD2/R/DD23/0147/20/2579/2539 | 2021-09-20 | Processing ,Machining & Realization of HPS3C Convergent Sub Assembly Nozzle Liners including coomposite profile Machining | 10 | 6.85 | 3.15 | 2026-11-30 | CPDC
ASL | ASL/31/21/4067/17/0022/0011 | 2022-05-06 | Procssing Of D1 Nozzle Liners Includes Composite Profile machining & Nozzle Integration | 4 | 2.7 | 1.3 | 2026-08-26 | CPDC
ASL | ASL/31/21/4067/17/0022/0011 | 2022-05-06 | Procssing Of D2 Nozzle Liners Includes Composite Profile machining & Nozzle Integration | 2 | 1.85 | 0.15 | 2026-08-26 | CPDC
ASL | ASL/DA1P/R/DA1P/0133/22/1063/1034 | 2023-09-15 | Bonding and SBU Layup of P1C Nozzle Liners | 5 | 3 | 2 | 2026-12-31 | CPDC
ASL | ASL/DA1P/R/DA1P/0133/22/1056/1039 | 2023-12-13 | Processing of P1C Nozzle Liners including composite profile machining and nozzle integration | 10 | 6.4 | 3.6 | 2027-12-31 | CPDC
ASL | ASL/DA1P/R/DA1P/0133/22/1056/1039 | 2023-12-13 | Processing of P2C Nozzle Liners including composite profile machining and nozzle integration | 10 | 6.4 | 3.6 | 2027-12-31 | CPDC
PGAD | PGAD/TD-RCI/AH/24-25/0009/50124 | 2024-10-16 | KV TVC ASSEMBLY | 4 | 0 | 4 | 2026-12-31 | Design
AADYAH | 2025260100 | 2025-12-08 | Flex seal proof pressure test fixture | 1 | 0 | 1 | 2026-06-06 | Design
AADYAH | 2025260129 R1 | 2026-03-23 | Metallic Hardware | 2 | 0 | 2 | 2026-06-30 | Design
AADYAH | 2025260129 R1 | 2026-03-23 | Fasteners Brackets & Turnbuckles | 2 | 0 | 2 | 2026-06-30 | Design
AADYAH | 2025260129 R1 | 2026-03-23 | Metallic Container with Vibration Pads | 2 | 0 | 2 | 2026-06-30 | Design
AADYAH | 2025260129 R1 | 2026-03-23 | One Time cost for tooling and Fixtures | 1 | 0 | 1 | 2026-06-30 | Design
ANSP | drdl/972/21/15k/2024/2176/2218P | 2025-08-13 | Section -1 Assembly | 9 | 0 | 9 | 2028-02-13 | IBRPTM
ANSP | drdl/972/21/15k/2024/2176/2218P | 2025-08-13 | Section -1 Tooling | 1 | 0 | 1 | 2028-02-13 | IBRPTM
ANSP | drdl/972/21/15k/2024/2176/2218P | 2025-08-13 | Section -1A Pocket Cover | 198 | 0 | 198 | 2028-02-13 | IBRPTM
ANSP | drdl/972/21/15k/2024/2176/2218P | 2025-08-13 | Section -1B Pocket Cover | 252 | 0 | 252 | 2028-02-13 | IBRPTM
ANSP | DRDL/9749/21/15LV/2024/0320/0336 | 2025-06-10 | Rocasin Lining for AIR Booster | 11 | 6 | 5 | 2026-12-10 | Nasik
ANSP | DRDL/9749/21/15LV/2024/0320/0336 | 2025-06-10 | Rocasin Lining for B-II Motor | 8 | 6 | 2 | 2026-12-10 | Nasik
THEJO | LIN/24-25/24050736-2 | 2025-03-12 | Lining of 2 mm Rocasin Base Layer | 4185 | 307.77 | 3877.23 | 2029-11-18 | SHAR
THEJO | LIN/24-25/24050736-2 | 2025-03-12 | Lining of 1 mm Rocasin Base Layer | 90 | 19.4 | 70.6 | 2029-11-18 | SHAR
THEJO | LIN/24-25/24050736-2 | 2025-03-12 | Lining of 2 mm Rocasin Base subsequent Layer | 38025 | 2210.83 | 35814.17 | 2029-11-18 | SHAR
THEJO | LIN/24-25/24050736-2 | 2025-03-12 | Lining of 1 mm Rocasin Base subsequent Layer | 2970 | 257.5 | 2712.5 | 2029-11-18 | SHAR
THEJO | LIN/24-25/24050736-2 | 2025-03-12 | Abrading Solvent cleaning Resin linging of Agni Sleeves | 3262.5 | 147 | 3115.5 | 2029-11-18 | SHAR
THEJO | LIN/24-25/24050736-2 | 2025-03-12 | Vaccum Bagging of Hardward | 4320 | 217.46 | 4102.54 | 2029-11-18 | SHAR
THEJO | LIN/24-25/24050736-2 | 2025-03-12 | Abrasion Vulcanised insuraltion surface for Hardware | 8775 | 264.45 | 8510.55 | 2029-11-18 | SHAR
THEJO | LIN/24-25/24050736-2 | 2025-03-12 | solvent cleaning spacer bellow bonding & LF Extn for Hardware | 8775 | 264.45 | 8510.55 | 2029-11-18 | SHAR
THEJO | LIN/24-25/24050736-2 | 2025-03-12 | Lining of rubber sheet with carbon cloth as composite Lining | 4185 | 133.1 | 4051.9 | 2029-11-18 | SHAR
SHAR | SDSC SHAR/SMP&ETF PURCHASE/SH2025P000920101 | 2025-07-28 | Contract for Rocasin Lining of Agni Motor HE Domes | 300 | 74 | 226 | 2029-11-18 | SHAR
ANSP | DRDL/8801/21/15K/2021/1902/1903P | 2021-12-03 | supply of EPDM Rubber for B1,B2 and B3 | 3000 | 1000 | 2000 | 2026-01-31 | UNIT-1
BDL | 3220009159 | 2021-12-13 | Insulation for Rocekt Motor Casing Assy | 6 | 0 | 6 | TO+45 Days | UNIT-1
BDL | 3220009159 | 2021-12-13 | Lining of Head Endcover Assy | 6 | 0 | 6 | TO+45 Days | UNIT-1
BDL | 3220009159 | 2021-12-13 | Linging of Igniter Canister Assy | 6 | 0 | 6 | TO+45 Days | UNIT-1
BDL | 3220009159 | 2021-12-13 | Lining of Nozzle Divergent Assy | 6 | 0 | 6 | TO+45 Days | UNIT-1
BDL | 3220009159 | 2021-12-13 | Linging of Intigrated Blast Tube | 6 | 0 | 6 | TO+45 Days | UNIT-1
BDL | 3220010770 | 2022-11-21 | Insulation for Rocekt Motor Casing Assy | 222 | 86 | 136 | FIM+3 Months | UNIT-1
BDL | 3220010770 | 2022-11-21 | Lining of Head Endcover Assy | 222 | 80 | 142 | FIM+3 Months | UNIT-1
BDL | 3220010770 | 2022-11-21 | Lining of Igniter Canister Assy | 222 | 80 | 142 | FIM+3 Months | UNIT-1
BDL | 3220010770 | 2022-11-21 | Lining of Nozzle Divergent Assy | 222 | 80 | 142 | FIM+3 Months | UNIT-1
BDL | 3220010770 | 2022-11-21 | Lining of Intigrated Blast Tube | 222 | 80 | 142 | FIM+3 Months | UNIT-1
SHAR-SPP | SDSC SHAR/SMPC-U2 PURCHASE/SH/2023P003700101 | 2024-01-31 | SUPPLY OF EXTRUDED ROCASIN RUBBER SLEEVES | 1764 | 200 | 1564 | 2027-01-31 | UNIT-1
SHAR | SDSC SHAR/SMPC-U1 PURCHASE/SH2023P009510101 | 2024-11-19 | supply of 2 mm thk uncured rocasin extruded sheet-2MM B/L | 5115 | 467.6 | 4647.4 | 2029-11-18 | UNIT-1
SHAR | SDSC SHAR/SMPC-U1 PURCHASE/SH2023P009510101 | 2024-11-19 | supply of 1mm thick extruded-Base layer | 110 | 0 | 110 | 2029-11-18 | UNIT-1
SHAR | SDSC SHAR/SMPC-U1 PURCHASE/SH2023P009510101 | 2024-11-19 | supply of 2mm thick extruded-subsequent layer | 46475 | 4111.305 | 42363.695 | 2029-11-18 | UNIT-1
SHAR | SDSC SHAR/SMPC-U1 PURCHASE/SH2023P009510101 | 2024-11-19 | supply of 1mm thick extruded-susequent layer | 3630 | 313.07 | 3316.93 | 2029-11-18 | UNIT-1
SHAR | SDSC SHAR/SMPC-U1 PURCHASE/SH2023P009510101 | 2024-11-19 | supply of rocasin sleeves-Agni | 3988 | 218 | 3770 | 2029-11-18 | UNIT-1
SHAR | SDSC SHAR/SMPC-U1 PURCHASE/SH2023P009510101 | 2024-11-19 | Rubber Lining for Vaccum Bagging | 5280 | 293.03 | 4986.97 | 2029-11-18 | UNIT-1
SHAR | SDSC SHAR/SMPC-U1 PURCHASE/SH2023P009510101 | 2024-11-19 | Rubber Lining abrasion of vulcanised insulation surface for H/W | 10725 | 496.15 | 10228.85 | 2029-11-18 | UNIT-1
SHAR | SDSC SHAR/SMPC-U1 PURCHASE/SH2023P009510101 | 2024-11-19 | Rubber Lining solvent cleaning spacer bellow bonding | 10725 | 496.15 | 10228.85 | 2029-11-18 | UNIT-1
SHAR | SDSC SHAR/SMPC-U1 PURCHASE/SH2023P009510101 | 2024-11-19 | Rubber Lining of rubber sheet with carbon cloth | 5115 | 739 | 4376 | 2029-11-18 | UNIT-1
BDL | 3220014253 | 2024-11-25 | Motor Casing Assembly with liner-VLSRSAM | 10 | 0 | 10 | T0+4months | UNIT-1
BDL | 3220014253 | 2024-11-25 | Head End Cover-VLSRSAM | 10 | 0 | 10 | T0+4months | UNIT-1
BDL | 3220014253 | 2024-11-25 | Igniter Canister Lining Assembly-VLSRSAM | 10 | 0 | 10 | T0+4months | UNIT-1
BDL | 3220014253 | 2024-11-25 | Nozzle Convergent Blast Tube Assembly-VLSRSAM | 10 | 0 | 10 | T0+4months | UNIT-1
BDL | 3220014253 | 2024-11-25 | Nozzle Divergent Assembly-VLSRSAM | 10 | 0 | 10 | T0+4months | UNIT-1
Skyroot | UA241-00002 | 2025-01-02 | Rocasin rubber sheet 2mm thk uncured | 200 | 150 | 50 | 2025-03-30 | UNIT-1
SHAR-SPP | SDSC SHAR/SMPC-U2 PURCHASE/SH2024P000360103 | 2025-04-17 | supply of 2mm thick extruded Rocasin Rubber Sheet -SPP | 36600 | 5400 | 31200 | 2029-04-16 | UNIT-1
SHAR-SPP | SDSC SHAR/SMPC-U2 PURCHASE/SH2024P000360103 | 2025-04-17 | supply of 1mm thick extruded Rocasin Rubber Sheet -SPP | 1605 | 155 | 1450 | 2029-04-16 | UNIT-1
ASL | GEMC-511687721732349 | 2025-06-03 | Un Vulcanized rocasin Rubber sheet | 1500 | 250 | 1250 | 2027-06-03 | UNIT-1
SKYROOT | AJ253-0032 | 2026-03-24 | Raman-I thrust chamber Assy | 10 | 0 | 10 | 2026-07-30 | UNIT-1
Skyroot | AJ247-00004 | 2024-07-05 | VK1 Retro Motor Nozzle assembly | 10 | 9 | 1 | 2024-08-04 | UNIT-1
Hemrl | HEMRL/26GM0681/SRP-III/GN/GEM | 2026-01-09 | Sleeve for Control Mould as per spec | 200 |  | 200 | 2027-01-09 | Unit-1
VSSC | 5562 2024P044700101 ¦ LO | 2024-10-30 | Filment wound product decelopment and fabrication of composite by random fiber compression moulding process | 3 | 0 | 3 | Intimation+60 Days | Unit-1A
VSSC | 5562 2024P044700101 ¦ LO | 2024-10-30 | Filment wound product decelopment and fabrication of composite by zero degree tape winding autoclave process | 3 | 0 | 3 | Intimation+60 Days | Unit-1A
VSSC | 5562 2024P044700101 ¦ LO | 2024-10-30 | Filment wound product moulding /winding tool assembly | 1 | 0 | 1 | Intimation+60 Days | Unit-1A
Aditya | PO/25-26/1862 | 2026-03-12 | Prop Travel Holder | 150 | 0 | 150 | 2026-08-09 | Unit-1A
Aditya | PO/25-26/1862 | 2026-03-12 | Antena Test Window | 300 | 0 | 300 | 2026-08-09 | Unit-1A
Aditya | PO/25-26/1862 | 2026-03-12 | GPS Window | 150 | 0 | 150 | 2026-08-09 | Unit-1A
Aditya | PO/25-26/1862 | 2026-03-12 | Cannister Front Lid | 150 | 0 | 150 | 2026-08-09 | Unit-1A
Aditya | PO/25-26/1862 | 2026-03-12 | Pusher Cylinder External | 300 | 0 | 300 | 2026-08-09 | Unit-1A
Aditya | PO/25-26/1862 | 2026-03-12 | Push Pole tube | 300 | 0 | 300 | 2026-08-09 | Unit-1A
ANSP | DRDL/9180/21/15K/2022/1989/2037P | 2023-05-16 | manfacturing and supply of Thermal Ptotection Dome( TP Dome | 20 | 9 | 11 | 2027-05-14 | Unit-2
PGAD | PGAD/TD-RCI/AM/23-24/K-15(B1)/50075 | 2024-04-26 | Manfacturing and supply of B1 Flex Nozzle Assembly | 5 | 0 | 5 | 2027-01-31 | Unit-2
PGAD | PGAD/TD-RCI/AM/23-24/K-15(B2)/50074 | 2024-04-26 | Manfacturing and supply of B2 Flex Nozzle Assembly | 5 | 0 | 5 | 2027-01-31 | Unit-2
ANSP | DRDL/9673/21/HSABV/2024/0010/0005 | 2024-12-06 | B1 FNS METALLIC CONTAINER WITH VIBRATION PADS | 3 | 0 | 3 | 2026-12-06 | Unit-2
RCI | RCI/25AT0117/RM2/RUDRAM-2/CMS-II | 2025-01-27 | R167 Nozzle Casing with Thermal insulation | 24 | 0 | 24 | 2027-02-03 | Unit-2
Godrej | 1900/1DR043479/JS9000195 | 2025-09-19 | M2B Nozzle wid Divergent Liner | 4 | 1 | 3 | FIM+30Days | Unit-2
Godrej | 1900/1DR043479/JS9000196 | 2025-09-19 | LS KV NOZZLE WITH Divergent | 3 | 0 | 3 | FIM+30Days | Unit-2
Godrej | 1900/1DR043479/JS9000190 | 2025-08-19 | LS KV NOZZLE WITH Divergent | 1 | 0 | 1 | FIM+30Days | Unit-2
PEL | SPD_4768 | 2025-10-17 | Nozzle End Assy -306 | 31 | 2 | 29 | 2025-12-16 | Unit-2
PEL | SPD_4767 | 2025-10-17 | Nozzle Assembly 240 | 9 | 2 | 7 | 2025-12-16 | Unit-2
AADYAH | 2025260100 | 2025-12-08 | flex seal including proof pressure testing | 3 | 0 | 3 | 2026-06-06 | Unit-2
AADYAH | 2025260100 | 2025-12-08 | Flex seal with thermal boot assembly | 3 | 0 | 3 | 2026-06-06 | Unit-2
PEL | SPD_4979 | 2026-01-29 | RMNEA 240 Nozzle Assembly Y-240 | 35 | 0 | 35 | 2026-07-30 | Unit-2
TATA | 5600002832 | 2026-02-10 | MRSAM-Jet Deflector with coating assembly | 1 | 0 | 1 | 2026-03-03 | Unit-2
Walchand | WACPL/RAPS/PREPREG/017/2025-26 | 2026-02-23 | Impregnation Rayon Based Carbon fabric with Phenolic resin | 525 | 0 | 525 | 2026-03-23 | Unit-2
Walchand | WACPL/RAPS/PREPREG/017/2025-26 | 2026-02-23 | Impregnation High Silica fabric with Phenolic resin | 40 | 0 | 40 | 2026-03-23 | Unit-2
SOLAR | 4500601363 | 2026-03-30 | E - GLASS & D 356 X 1730 MM | 4 | 0 | 4 |  | Unit-2
AADYAH | 2025260129 R1 | 2026-03-23 | manufacturing and supply of Flex Nozzle assembly including integration | 1 | 0 | 1 | 2026-06-30 | Unit-2
ANSP | DRDL/9673/21/HSABV/2024/0010/0005 | 2024-12-06 | MANFACTURING & SUPPLY OF B1 FNS ASSEMBLY INCUDING FLEX SEAL AND NOZZLE INTEGRATION | 3 | 0 | 3 | 2026-12-06 | Unit-2
Oka Basu | OMBT/RAPS-03/26-27 | 2026-04-15 | Carbon components | 1 |  | 1 | 2026-06-14 | Unit-2
DRDL | DRDL/PGLRSAM/1701/31P/26/432/0488 | 2026-05-21 | M1 POTABLE JET DEFLECTOR 60T WITH COMPRESSION MOULED ROSETTE GPH | 2 |  | 2 | 2026-08-20 | Unit-2
TATA | 5600003150 | 2026-05-20 | Glass Phenolic for Jet Deflector (M1) | 1 |  | 1 | FIM+1 month | Unit-2
Skyroot | AJ23N-00001 | 2023-11-01 | S2 Nozzle Assembly ( Flight) | 2 | 1 | 1 | 2024-01-15 | Unit-3
ANSP | DRDL/9348/21/15K/2022/2051/2117P | 2024-01-18 | Manufacturing & Supply of B1 FNS Assembly Including Flex Seal | 6 | 4 | 2 | 2027-01-18 | Unit-3
ANSP | DRDL/9348/21/15K/2022/2051/2117P | 2024-01-18 | Manufacturing & Supply of B2 FNS Assembly Including Flex Seal | 6 | 4 | 2 | 2027-01-18 | Unit-3
Aditya | PO/24-25/0291 | 2024-07-10 | Lining of Motor Casing-P197 | 9 | 5 | 4 | 30+FIM | Unit-3
Aditya | PO/24-25/0291 | 2024-07-10 | Lining of Nozzele--P197 | 11 | 5 | 6 | 30+FIM | Unit-3
BEML | 6930008257 | 2024-08-09 | P1 MOTOR WITH LINER | 30 | 1 | 29 | 2025-09-29 | Unit-3
BEML | 6930008257 | 2024-08-09 | P2 MOTOR WITH LINER | 30 | 1 | 29 | 2025-09-29 | Unit-3
BEML | 6930008257 | 2024-08-09 | LS KV NOZZLE WITH LINER ASSY | 30 | 1 | 29 | 2025-09-29 | Unit-3
BEML | 6930008257 | 2024-08-09 | SUPPORT GRID WITH LINER | 30 | 1 | 29 | 2025-09-29 | Unit-3
BEML | 6930008257 | 2024-08-09 | PSD WITH LINER | 30 | 1 | 29 | 2025-09-29 | Unit-3
BEML | 6930008257 | 2024-08-09 | KV DOME WITH LINER | 30 | 1 | 29 | 2025-09-29 | Unit-3
BEML | 6930008257 | 2024-08-09 | PC TUBE WITH LINER | 30 | 1 | 29 | 2025-09-29 | Unit-3
BEML | 6930008257 | 2024-08-09 | SP 16 RING (SG) | 30 | 1 | 29 | 2025-09-29 | Unit-3
BEML | 6930008257 | 2024-08-09 | EPDM COVER | 30 | 1 | 29 | 2025-03-29 | Unit-3
Skyroot | AJ241-00003 | 2025-01-27 | VK-1 S3 FLEX NOZZLE ASSEMBLY | 2 | 1 | 1 | 2025-03-30 | Unit-3
DRDL | DRDL/26AT0045/VL-SRSAM/ 78/ DOMR / 78469 | 2026-01-22 | EPDM Lining of Rocket Motor Casing & Nozzle)-ADP | 4 | 0 | 4 | 2026-07-03 | Unit-4
ASL | ASL/DD2/R/DD23/0133/20/2505/2573 | 2021-01-19 | Rocasin Rubber Lining on S1C Intermediate Dome And Machining | 10 | 7 | 3 | 2026-12-30 | Unit-4
VSSC | B213 2023P063270101I LO | 2024-05-16 | EPDM-Non Metallic Bellow | 1 | 0 | 1 | 2024-09-14 | Unit-4
VSSC | 1710 2023P04820101 I LO | 2024-06-03 | Development /Trail Batch S200 Thermal Boot | 2 | 1 | 1 | Clearance + 180 Days | Unit-4
VSSC | 1710 2023P04820101 I LO | 2024-06-03 | Production Batch of S200 Thermal Boots | 5 | 0 | 5 | Clearance + 180 Days | Unit-4
Skyroot | UC24D-00002 | 2024-12-03 | S3 Igniter Insulation Boot | 8 | 7 | 1 | 2024-12-30 | Unit-4
ANSP | DRDL/9615/21/15K/2024/2146/2184P | 2024-12-30 | Base Dome-1& Base Dome-2 for Thermal Lining | 15 | 10 | 5 | 2026-06-30 | Unit-4
Skyroot | AJ24N-00003 | 2024-11-07 | 02A-03-AB1-000- S3 NOZZLE SUBMERGED SUB ASSEMBLY- | 2 | 1 | 1 | 2025-01-30 | Unit-4
Brahmos | SODEL/0008/2425 | 2025-01-16 | PJ10_321-01-01-00-00, B2 Shel Assy With liner | 30 | 14 | 16 | 2026-07-31 | Unit-4
Brahmos | SODEL/0008/2425 | 2025-01-16 | PJ10_321-03-01-01-01, B1 outer Shel Assy With EPDM liner | 30 | 14 | 16 | 2026-07-31 | Unit-4
Brahmos | SODEL/0008/2425 | 2025-01-16 | PJ10_321-02-01-00-00, Dome with liner | 30 | 14 | 16 | 2026-07-31 | Unit-4
Brahmos | SODEL/0008/2425 | 2025-01-16 | DOSP/SPD/PJ10/SK-321-01,HTM Nozzle End Assy | 30 | 9 | 21 | 2026-07-31 | Unit-4
Brahmos | SODEL/0008/2425 | 2025-01-16 | PJ10_321-03-01-04-00, B1 Inner shell assy with liner | 30 | 13 | 17 | 2026-07-31 | Unit-4
Brahmos | SODEL/0008/2425 | 2025-01-16 | DOSP/SPD/PJ10/SK-321-02,LTM Nozzle End Assy | 30 | 9 | 21 | 2026-07-31 | Unit-4
Brahmos | PODEL/00316/24-25 | 2025-01-16 | PJ10_321-02-02-00-00, HTM Igniter Assembly | 30 | 20 | 10 | 2026-07-31 | Unit-4
VSSC | 521B 2024po50570101! LO | 2025-03-26 | Filment wound Product Fabrication of Cryotank | 3 | 0 | 3 | 2025-09-20 | Unit-4
Skyroot | UC259-00022 | 2025-09-11 | S1 Igniter Insulation Boot | 3 | 0 | 3 | 2025-10-30 | Unit-4
Skyroot | UC259-00023 | 2025-09-11 | vk1 s2 igniter insulation boot | 4 | 0 | 4 | 2025-10-30 | Unit-4
Skyroot | UC259-00024 | 2025-09-11 | S3 Igniter Insulation Boot | 3 | 0 | 3 | 2025-10-30 | Unit-4
DRDL | drdl/24/08P/25/0197/43875/dosrp | 2025-11-04 | Lining of CC 180rocket motor casing and nozzle assembly | 2 | 0 | 2 | 2026-08-31 | Unit-4 | PDC EXT. REQUEST SENT TILL 31-08-26
BDL | 3220016545 | 2026-01-22 | Motor with Liner-QRSAM | 3 | 0 | 3 | FMI+4 months | Unit-4
BDL | 3220016545 | 2026-01-22 | Motor Casing Assembly-QRSAM | 3 | 0 | 3 | FMI+4 months | Unit-4
BDL | 3220016545 | 2026-01-22 | Nozzle with Divergent-QRSAM | 3 | 0 | 3 | FMI+4 months | Unit-4
ICOMM | DEF/D/PO/25-26/0946 | 2026-02-26 | Booster motor casing with liner | 6 | 0 | 6 | 2026-12-31 | Unit-4
ICOMM | DEF/D/PO/25-26/0946 | 2026-02-26 | Booster Nozzle casing with liner assembly | 6 | 0 | 6 | 2026-12-31 | Unit-4
ICOMM | DEF/D/PO/25-26/0946 | 2026-02-26 | Booster Igniter Mount with liner assembly | 6 | 0 | 6 | 2026-12-31 | Unit-4
ICOMM | DEF/D/PO/25-26/0946 | 2026-02-26 | Booster canister with liner assembly | 6 | 0 | 6 | 2026-12-31 | Unit-4
ICOMM | DEF/D/PO/25-26/0946 | 2026-02-26 | Sustiner Nozzle casing with liners Assembly | 6 | 0 | 6 | 2026-12-31 | Unit-4
ICOMM | DEF/D/PO/25-26/0946 | 2026-02-26 | Booster Igniter Mount with liner assembly-1 | 7 | 0 | 7 | 2026-12-31 | Unit-4
ICOMM | DEF/D/PO/25-26/0946 | 2026-02-26 | Booster canister with liner assembly-1 | 7 | 0 | 7 | 2026-12-31 | Unit-4
ICOMM | DEF/D/PO/25-26/0946 | 2026-02-26 | Sustiner motor casing with liners refurbishement | 6 | 0 | 6 | 2026-12-31 | Unit-4
Adani | 4500401496 | 2026-04-02 | Removal of Old Liner and refurbishment of Sustainer motor casing and EPDM lining of sustainer motors | 4 | 0 | 4 | 2026-07-30 | Unit-4
Adani | 4500401496 | 2026-04-02 | Removal of Old Liner & refurbishment of Booster motor & EPDM Lining | 4 | 0 | 4 | 2026-07-30 | Unit-4
RCI | RCI/27AT0004/SF VSH/GN/CMS-II | 2026-04-02 | Lining of SFVSH rocket motor assembly | 10 | 0 | 10 | 2026-10-06 | Unit-4
PGAD | PGAD/77410/01/LPC/26-27/0440 | 2026-04-23 | Old Rocasin Rubber Removal from Motor Case | 2 |  | 2 | 2026-06-25 | Unit-4
BEL | 4300036355 | 2026-04-16 | EPDM Rubber Lining of Pralay Motors | 2 |  | 2 | FIM+2 months | Unit-4
SOLAR | 4500007207 | 2026-04-15 | Removal & Application of LRSAM Liner-P1 & P2 Motor | 1 |  | 1 | 2026-08-13 | Unit-4
Brahmos | SCOHYD/26-27/4027 | 2026-04-28 | PJ10_321-01-01-00-00, B2 Shel Assy With liner | 30 |  | 30 | 2028-03-31 | Unit-4
Brahmos | SCOHYD/26-27/4027 | 2026-04-28 | PJ10_321-03-01-01-01, B1 outer Shel Assy With EPDM liner | 30 |  | 30 | 2028-03-31 | Unit-4
Brahmos | SCOHYD/26-27/4027 | 2026-04-28 | PJ10_321-02-01-00-00, Dome with liner | 30 |  | 30 | 2028-03-31 | Unit-4
Brahmos | SCOHYD/26-27/4027 | 2026-04-28 | DOSP/SPD/PJ10/SK-321-01,HTM Nozzle End Assy | 30 |  | 30 | 2028-03-31 | Unit-4
Brahmos | SCOHYD/26-27/4027 | 2026-04-28 | PJ10_321-03-01-04-00, B1 Inner shell assy with liner | 30 |  | 30 | 2028-03-31 | Unit-4
Brahmos | SCOHYD/26-27/4027 | 2026-04-28 | DOSP/SPD/PJ10/SK-321-02,LTM Nozzle End Assy | 30 |  | 30 | 2028-03-31 | Unit-4
ANSP | DRDL/9927/21/15K/2025/2216/2259P | 2026-05-13 | LTB CASING ASSY WITH LINER & NE GRID | 48 |  | 48 | 2027-11-13 | Unit-4
ANSP | DRDL/9927/21/15K/2025/2216/2259P | 2026-05-13 | LTB HEAD END ASSEMBLY WITH LINER | 48 |  | 48 | 2027-11-13 | Unit-4
DRDL | DRDL/25AT0034/ET-LDHCM/75/DOMR | 2024-06-19 | Manufacturring and supply of H1 FNS Assembly including Flex Seal and nozzle Integration | 5 | 2 | 3 | 2026-07-31 | Unit-5
ANSP | DRDL/8816/21/15F/2021/0714/0889F | 2024-07-19 | Manfacturing of S1 CRMC | 4 | 0 | 4 | 2027-11-30 | Unit-5
Brahmos | SCOHYD/24-25/0008 | 2024-07-15 | SK 341 CANSISTER MARK-IV | 2 | 0 | 2 | 2026-08-30 | Unit-5
Brahmos | SCOHYD/24-25/0008 | 2024-07-15 | SK 341 CANSISTER MARK-IV | 3 | 0 | 3 | 2026-08-30 | Unit-5
PGAD | PGAD/7741/01/FE/24-25/0105/41958 | 2025-07-04 | Composite Rocket Motor Casing with EPDM Liner for P191 | 2 | 0 | 2 | 2026-12-31 | Unit-5
NSTL | NSTL/26AT0047/GN/CMS-III/LP-I/25-26/LP-1/4059 | 2026-02-20 | manufacture and supply of Dia 380*2700mm long composite shell assembly with containers for air droppable containers | 10 | 0 | 10 | 2027-02-01 | Unit-5
BDL | 3220017037 | 2026-04-17 | launchtube assembly forMPATGM | 10 |  | 10 | 2026-07-09 | Unit-5
ANSP | DRDL/10003/21/15F/2025/1135/1063F | 2026-04-20 | MANFACTURING AND SUPPLY OF S2 CRMC | 4 |  | 4 | 2028-04-20 | Unit-5
|  |  | Total |  | 18881.265 | 196985.235
Formulas:
PDC = +[Date]+180
PDC = [Date]+60